## Backlog
ID | Context | Description | PO
US-1 | I want to access to a list of existing armors | Filtering list with existing armors | Confirmed players, novice players
US-11 | The user can browse the complete list of existing armors | Shows a list of all existing armors from the API | Confirmed players, novice players
US-12 | The user can filter the armor list by name | When entering text in a TextBox the user can filter the list to display armors containing the text written | Confirmed players, novice players
US-13 | The user can filter the armor list by type | Filters the list by a selected Armor type in a given list
US-14 | The user can filter the armor list for specific armorsets | Filters the list by a selected Armorset type in a given list
US-15 | The user can filter the armor list by rarity | Filters the list by a selected Rarity type in a given list
US-16 | The user can select and get details of a specific armor | When clicking on an armor, the user has access to more specific informations about the piece of armor (defense, resistance, etc.)
US-17 | The user can add the currently selected armor piece to its current build | The user has the choice of adding selected armor piece to its current build
Tâches techniques
| Environneent de développement | 5h
DSL
Récupérer les données de Xtend
Création d'un front
Afficher les données
Estimer le temps
US-2
US-21 | Générer le code de l'API pour extraire toutes les armes
US-22 | Récupérer les données et les afficher
US-23 | I want to access a list of weapons | Filtering list with existing weapons | Confirmed players, novice players
US-24 | The user can browse the complete list of existing weapons | Shows a list of all existing weapons from the API | Confirmed players, novice players
US-25 | The user can filter the armor list by name | When entering text in a TextBox the user can filter the list to display armors containing the text written | Confirmed players, novice players
US-26 | The user can filter the armor list by type | Filters the list by a selected Armor type in a given list
US-27 | The user can filter the armor list for sharpness | Filters the list by a selected Sharpness attribute
| The user can filter the armor list by rarity | Filters the list by a selected Rarity type in a given list
US-3 | The user can select and get details of a specific armor | When clicking on an armor, the user has access to more specific informations about the piece of armor (defense, resistance, etc.)
US-31 | The user can add the currently selected armor piece to its current build | The user has the choice of adding selected armor piece to its current build
US-32
US-33 | I want to create my own build | Panel for build creation | Confirmed players
US-34 | The user can access its current build | Displays every piece constituting the current build
| The user can save its current build | The user is able to persist his current build via a Save button, to use it for later purposes
US-4 | The user can load its current build | Displays a list of previously saved builds and allows the user to load it
US-5 | The user can delete pieces of equipment from the current build | On each equipment piece, there is a delete button allowing the user to remove this equipement from the current build.
US-6
| I want to access to a list of existing talents | Filtering list with existing talents | Confirmed players, novice players
| I want to access to a list of existing charms | Filtering list with existing charms | Confirmed players, novice players
| I want to access a list of decorations | Panel for build generation with caracteristics selection | Novice players

## PO
User ID | User role | Context
1 | Confirmed player | This player plays at MHW since the release of the game and he wants to fight high level monsters. So he needs to find his armor's set with charms and decorations, generate his armor's set with talents that he selects
2 | Novice player | This player started the game 2 weeks ago and he doesn't know the game very well so he needs to generate his armor's set with talents that he selects to advice him.